## Tasks
TASK | ASSIGNED TO | COMMENTS | COMPLETE
PRE-EVENT OPENING TASKS
Get permission from local council/landowner to use venue.
Complete TLI Application to Promote an Event Form. |  |  |  |  | http://www.tlicycling.org.uk/Downloads.aspx
Complete TLI Membership Application Form (as Organiser)
Create event poster/promotional material.
Set up event on Entry Central |  | Email Ian McLaughlin at Entry Central |  | Log in here | https://www.entrycentral.com/organiser/index.php
Get out on course recce, clearance etc
Create course map post course recce
EVENT PERSONNEL
Get timing arranged |  | Mark Young (mylaps to do timing. Cost £375 + £1 per rider
Get commentator & PA system
Get first aiders
COURSE EQUIPMENT
Get course stakes
Get course tape
Get course scrim and posts
Get course barriers and posts
Get fluoro tempo spray paint
EVENT EQUIPMENT
Get arm numbers and pins
Get folding table and chairs for sign on
Get sign on tent
Get notice board for outside the sign on tent
Get race radios
Get air horn /whistle/klaxon.gun for the start
Get buckets/bags for rider excess start line clothing
Get lap numbers
Get last lap bell
Get checkered flag
Get cash prize and envelopes for podium places
Get medals for podium places
Get podium place drinks
Get podium/make shift podium
Get bibs/hats/horns/whistles etc for marshals
Get sponsor banners for the course
Get food van arranged.
Get toilets arranged
Get signage to warn park users of the forthcoming race
Get signage to direct riders from car parks to course
PRE-EVENT TASKS
Send Rider Information Pack out via www.albannach.cc
Send Marshal Information Pack out via email
Check TLI numbers against TLI register
Send Risk Assessment to TLI |  | Send 2 days before event
Get copies of Combined Event Entry & Day Membership Form for the under 18's signed, printed and returned before the race. No form = no race. |  |  |  | Under 18
Populate the Standard Registration Sheet form for pre-entries |  | If using Mark Young he will usually do this for you.
POST-EVENT TASKS
Post results |  | Mark does via mylaps. Spread about via event websites and social media accounts. Email directly to participants.
Complete Injury / Accident / Incident Report Form (if required) |  | Return to Dave Moss if required.
Pay for timing
Pay for commentry and PA system
Pay for use of RGP
Pay for first aiders
Return Event Return Form including completed Standard Registration Sheets, Day Membership Forms and cheque for Dave Moss levys to TLI |  | Return to Dave Moss. Day membership form not required as long as they have signed the waiver on the standard registration sheet. To be done 7 days after the event. Fee not to include participants that have not signed on or turned up.

## Profit - Loss
INSTRUCTIONS - Fill in the yellow highlighted cells below only
Profit/Loss | 0
Total income | 0 | Total Costs | 0
Entrants |  | Total Prize Fund | 0
TLI member entrants | 0
Non-TLI member entrants | 0 | A RACE
Total entrants | 0 | M1
M2
Sponsorship |  | M3
Donation from …. | 0
Donation from …. | 0 | F1
Donation from …. | 0 | F2
Donation from …. | 0 | F3
Donation from …. | 0
Donation from …. | 0 | B RACE
Donation from …. | 0 | M1
Donation from …. | 0 | M2
Total non-entry income | 0 | M3
Entry fees |  | F1
TLI member entrants | 15 | F2
Non-TLI member entrants | 20 | F3
Levies |  | Costs (not inc levies) | 0
Entry Central booking fee per TLI entrant | 0.75
Entry Central booking fee per non-TLI entrant | 1
Super Quaich Series levy per entrant | 1
TLI levy per entrant | 5
Entry totals
TLI member entrants | 0
Non-TLI member entrants | 0
Entry Central booking fees | 0
Super Quaich Series levies | 0
TLI levies | 0
Net entry income | 0
Post Event
Non-TLI Riders that DNS | 0
Total TLI levys | 0
Surplus from DNS | 0
0
Note on C11: jcameron: Confirm these before start to ensure proper TLI funds go to Dave Moss (at TLI)